## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| SunKids System | Basel B | 2020-07-01 | 2020-08-06 |  | 15% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Build DataBase |  | Basel B |  | 2020-07-01 | 2020-07-14 | 14 | In Progress
| Kids' Table |  | Hozifa A |  | 2020-07-01 | 2020-07-05 | 5 | Complete
| Card's table |  | Hozifa A |  | 2020-07-06 | 2020-07-08 | 3 | In Progress
| logs' tables |  | Basel B |  | 2020-07-08 | 2020-07-14 | 7 | Not Started
| Create GUI |  | Hozifa A |  | 2020-07-16 | 2020-08-05 | 21 | Not Started
| Design |  | Hozifa A |  | 2020-07-16 | 2020-07-25 | 10 | Not Started
| Create interfaces and Buttons |  | Hozifa A |  | 2020-07-19 | 2020-07-29 | 11 | Not Started
| Integrate with DB |  | Basel B |  | 2020-07-26 | 2020-08-05 | 11 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET